## Gantt
CLAIMS OF TAMRIEL · Gantt Chart · COT_KRKE_2026
PROJECT Claims of Tamriel — Cross-Platform RPG Knowledge Base PROJECT MANAGER Atakan Kayı TEAM Atakan Kayı · Ceyda Uyar · Yiğit Ak DURATION 12 Weeks (W1–W12) + W13 Next Universe COURSE KRKE — University of Bologna
[6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [24 empty] | PHASE THREE | [14 empty] | PHASE FOUR |  |  |  |  | PHASE FIVE ↻
WBS | TASK TITLE | OWNER | START | END | DUR | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 ↻
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
PHASE ONE — Research & Requirements
Initiation | bar: WEEK 1 M to WEEK 2 F; WEEK 7 M to WEEK 11 F
1.1 | Stakeholder analysis & user groups | Atakan | D1 | D2 | 2 | bar: WEEK 1 M to WEEK 1 T; WEEK 7 M to WEEK 8 F
1.2 | Project Charter & success criteria | Atakan | D1 | D5 | 5 | bar: WEEK 1 M to WEEK 1 F; WEEK 7 M to WEEK 8 F
Requirements | bar: WEEK 1 M to WEEK 2 F; WEEK 7 M to WEEK 11 F
2.1 | User stories per user group | Atakan | D6 | D10 | 5 | bar: WEEK 2 M to WEEK 2 F; WEEK 7 M to WEEK 8 F
2.2 | SRS drafting & prioritisation | Atakan | D11 | D15 | 5 | bar: WEEK 3 M to WEEK 3 F; WEEK 7 M to WEEK 8 F
2.3 | Requirements review & sign-off | All | D15 | D15 | 1 | bar: WEEK 3 F; WEEK 7 M to WEEK 8 F
PHASE TWO — Engineering & Knowledge Population
Sprint 1 — Lore Research | bar: WEEK 1 M to WEEK 2 F; WEEK 7 M to WEEK 11 F
3.1 | SPRINT 1 — Skyrim full lore scan | All | D11 | D30 | 20
3.2 | In-game book reading & classification | Ceyda | D16 | D30 | 15 | bar: WEEK 4 M to WEEK 8 F
3.3 | Faction histories & motivations | Atakan | D21 | D30 | 10 | bar: WEEK 5 M to WEEK 8 F
Sprint 2 — Synthesis & Ontology | bar: WEEK 1 M to WEEK 2 F; WEEK 7 M to WEEK 11 F
4.1 | SPRINT 2 — Item × claim cross-check | Ceyda | D31 | D40 | 10 | bar: WEEK 7 M to WEEK 8 F
4.2 | Moral-compass positioning draft | Atakan | D31 | D40 | 10 | bar: WEEK 7 M to WEEK 8 F
4.3 | ClaimType taxonomy & SKOS scheme | Atakan | D36 | D40 | 5 | bar: WEEK 7 M to WEEK 8 F
5.1 | OWL class hierarchy & properties | Atakan | D36 | D45 | 10 | bar: WEEK 7 M to WEEK 9 F
5.2 | OWL restrictions & disjointness | Atakan | D41 | D45 | 5 | bar: WEEK 7 M to WEEK 9 F
5.3 | External vocab alignments (FOAF/PROV) | Atakan | D41 | D45 | 5 | bar: WEEK 7 M to WEEK 9 F
5.4 | Knowledge population — individuals | Ceyda | D41 | D50 | 10 | bar: WEEK 7 M to WEEK 10 F
PHASE THREE — Interface, Validation & Documentation
6.1 | 5 SPARQL competency questions | Ceyda | D46 | D50 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 10 M to WEEK 10 F
6.2 | Reasoner consistency check | Atakan | D46 | D50 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 10 M to WEEK 10 F
6.3 | Usability check — 3 user profiles | All | D51 | D55 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
7.1 | Interactive website (index.html) | Yiğit | D41 | D55 | 15 | bar: WEEK 7 M to WEEK 11 F
7.2 | Moral-compass visual & faction cards | Yiğit | D51 | D55 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
7.3 | Cross-device & accessibility pass | Yiğit | D56 | D60 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 12 M to WEEK 12 F
8.1 | SRS, testing doc, use case | Atakan | D51 | D55 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 11 M to WEEK 11 F
8.2 | User manual & slideshow | Atakan | D56 | D60 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 12 M to WEEK 12 F
PHASE FOUR — Delivery
Sprint 3 — Final | bar: WEEK 1 M to WEEK 2 F; WEEK 7 M to WEEK 11 F
9.1 | SPRINT 3 — Final review & polish | All | D56 | D60 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 12 M to WEEK 12 F
9.2 | Version tagging & submission ★ | All | D60 | D60 | 1 | bar: WEEK 7 M to WEEK 8 F; WEEK 12 F
PHASE FIVE — Next Universe Selection ↻
10.1 | Game universe selection research | All | D61 | D65 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 13 ↻ M to WEEK 13 ↻ F
10.2 | Feasibility & lore depth assessment | Atakan | D61 | D65 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 13 ↻ M to WEEK 13 ↻ F
10.3 | Source availability check | Ceyda | D61 | D65 | 5 | bar: WEEK 7 M to WEEK 8 F; WEEK 13 ↻ M to WEEK 13 ↻ F
10.4 | ↻ Cycle repeats from Phase 1 upon selection | All | D65 | D65 | 1 | bar: WEEK 7 M to WEEK 8 F; WEEK 13 ↻ F
↻ Upon selection of the next RPG universe, the full project cycle restarts from Phase 1. The ontology pattern (Claim · Holder · ClaimType · Conflict Relation) is domain-neutral and reusable across any game world.