# Project Charter

| Project Name | Claims of Tamriel — OWL Ontology of Contested Narratives in The Elder Scrolls V: Skyrim |
| --- | --- |
| Project ID | COT_KRKE_2026 |
| Grantor or Customer | Main stakeholder (customer): Knowledge Representation & Knowledge Extraction (KRKE) course, University of Bologna. Other key stakeholders: course instructor and evaluators, fellow students reviewing the model, and end users of the interactive documentation website. |

| Document version | Date | Contributor | State |
| --- | --- | --- | --- |
| 1.0 | 15.06.2026 | Atakan Kayı, Ceyda Uyar, Yiğit Ak | Draft for review |

## Project Description

This project plans and manages the design, implementation, and documentation of an OWL ontology that models competing and irreconcilable narratives within the fictional world of The Elder Scrolls V: Skyrim. Rather than encoding lore as established fact, the system models the structure of disagreement itself — who claims what, against whom, on what grounds, and through which kind of logical opposition. The architecture is intentionally domain-neutral: the same modelling pattern (Claim, Holder, ClaimType, three typed conflict relations) generalises to news media bias, legal testimony, or historical revisionism. The project deliverables include the ontology file, SPARQL competency queries, and a self-contained interactive documentation website.

## Project Scope

OWL ontology serialised in Turtle (.ttl) with 7 mutually disjoint classes, 16 Claim individuals organised as 8 dispute pairs, 8 Factions, 12 Characters, and 11 SKOS ClaimType concepts.

Three typed conflict relations (contradicts, disputes, denies) with formal OWL property characteristics (symmetric, irreflexive) and one property-chain axiom inferring hasOpposingHolder automatically.

OWL restrictions on the Claim class enforcing a holder, a ClaimType, and a description for every individual.

External vocabulary alignments: foaf:Person, foaf:Group, schema:Place, prov:Entity, and prov:wasAttributedTo.

Five SPARQL competency questions validating the design: faction conflict matrix, neutral character detection, directional denial chains, and more.

A fully self-contained interactive project website (index.html) with animated class diagram, all 8 dispute pairs, competency queries, and SKOS hierarchy visualisation.

Project management artefacts: Project Charter, Gantt diagram, SRS, architecture diagrams, sample use case, testing methodology, user manual, and slideshow.

## Deliverable List

Project Charter

Gantt diagram

Software Requirements Specification (SRS)

System / application structure diagram adapted to the ontology development workflow

Sample Use Case

Testing methodology description and at least one test case

Slideshow presenting the development process

User manual for a key interaction flow (interactive website)

Final artifact package: skyrim_ontology_v5_0.ttl, index.html, README

## Constraints

Academic scope: The project is developed within a single-semester course; time, team size, and review cycles are limited.

Fictional domain: Evidence is drawn from curated lore sources (UESP Wiki, CC BY-SA); modelling decisions must prioritise internal consistency and explainability over empirical correctness.

Epistemic neutrality requirement: The ontology must not declare any claim correct or any faction authoritative; every assertion must remain relativised to its holder.

No dynamic backend: The documentation layer is a static, self-contained HTML file — no server, database, or build step is involved.

Reasoning compatibility: The ontology must remain within OWL 2 DL to ensure reasoner compatibility (HermiT, Pellet).

## Risk Analysis

| Key Risks | Mitigations |
| --- | --- |
| Scope creep — adding more claims, characters, or sub-domains beyond the 8 dispute pairs (P: High, I: High) | Freeze the MVP scope around the current dispute set; treat new additions as Nice-to-have only after core quality is confirmed. |
| Conceptual inconsistency — class restrictions or property characteristics producing unintended inferences (P: Medium, I: High) | Validate every structural addition in Protégé before committing; run the OWL reasoner incrementally throughout development. |
| CQ–ontology misalignment — competency questions failing to return expected results (P: Medium, I: High) | Define competency questions before populating individuals and use them as acceptance criteria during modelling. |
| Documentation gap — technically strong ontology but difficult for evaluators to interpret (P: Medium, I: Medium) | Use the interactive website, named-individual tables, and explicit non-obvious-findings section to make reasoning transparent. |
| Team coordination — uneven progress across ontology, SPARQL, and web tasks (P: Medium, I: Medium) | Assign clear ownership by role; synchronise around a single versioned .ttl file; milestone-based internal reviews. |

## Work Breakdown Structure

High-level WBS — detailed timing in the Gantt diagram:

1. Initiation

1.1  Stakeholder analysis and objectives

1.2  Project charter and definition of success criteria

2. Requirements and Modelling Goals

2.1  Identify competency questions and intended query outcomes

2.2  Define modelling principles (epistemic neutrality, claim–holder structure, conflict relation semantics)

2.3  Requirements review and sign-off

3. Ontology Design

3.1  Define class hierarchy and mutual disjointness axioms

3.2  Define object properties, data properties, and OWL restrictions on Claim

3.3  Design SKOS ClaimType concept scheme

3.4  Establish external vocabulary alignments (FOAF, PROV-O, Schema.org)

4. Knowledge Population

4.1  Create Faction, Character, City, Race, and Item individuals

4.2  Encode 8 contested Claim pairs with evidence, source links, and evidence-strength scores

5. Validation and Querying

5.1  Test ontology consistency with OWL 2 DL reasoner

5.2  Develop and verify all 5 SPARQL competency questions

5.3  Confirm emergent inferences (e.g. hasOpposingHolder via property chain)

6. Documentation and Interface

6.1  Write README with ontology stats, design rationale, and usage instructions

6.2  Build interactive website (index.html) — class diagram, dispute pairs, CQs, SKOS viewer

6.3  Prepare diagrams, examples, and non-obvious findings for evaluation

7. Verification and Delivery

7.1  Produce SRS, testing document, use case, and user manual

7.2  Final review, version tagging, and course submission

## Resources

Human resources:

| Role | Contributor |
| --- | --- |
| Ontology Design & Knowledge Modelling | Atakan Kayı |
| SPARQL & Knowledge Extraction | Ceyda Uyar |
| Ontology Engineering & Web | Yiğit Ak |

In a small academic team, project management, QA, and documentation responsibilities are shared across all three contributors. No external procurement, licensing fees, or infrastructure services are required beyond open-source tooling (Protégé, Apache Jena/GraphDB, a standard web browser).

## Financial Budget

This is an academic project; the operational budget consists of team effort and open-source tool usage rather than monetary expenditure. The indicative effort distribution across work packages is:

| Work Package | Effort Share |
| --- | --- |
| Project management & documentation | 10% |
| Ontology modelling & semantic design | 35% |
| SPARQL querying & validation | 20% |
| Web documentation & interface development | 20% |
| Testing, revision & presentation | 15% |

If a monetary estimate is required by the instructor, the total can be expressed as person-hours × a standard academic hourly rate.

| Work Package | Effort Share | Estimated Hours | Cost (€15/hr) |
| --- | --- | --- | --- |
| Project management & documentation | 10% | 21.6 h | €324 |
| Ontology modelling & semantic design | 35% | 75.6 h | €1,134 |
| SPARQL querying & validation | 20% | 43.2 h | €648 |
| Web documentation & interface development | 20% | 43.2 h | €648 |
| Testing, revision & presentation | 15% | 32.4 h | €486 |
| Contingency buffer | — | — | €324 |
| Total | 100% | 216 h | €3,564 |